## Sheet1
Risk Assessment
Risk | Description | Probability | Severity | Owner | Mitigation
EC2 instance failiure | The EC2 instnace hosting the applicaiton is currently being held on a single instance. Any failuires with this instance then the applicaiton will be unavailable | Medium | Critical | Alex Bradford | Enable health checks on the instances to monitor. Enable Auto scaling groups to spin up/down instances as required
AWS AZ Failiure | The applicaiton is currently being hosted on instances within a single availability zone. This is not best practice as if there are any issues with AWS and the availability zone goes down, than the application will not be accessible | Low | Critical | AWS/Alex Bradford | Create new subnet in new AZ/ Enable autoscaling groups to add EC2 instances into this subnet. Create load balancer to be able to direct traffic and monitor health
SQL Injection | Improper hardending of the database could leave it exposed to an SQL injection where a harmful script is loaded into and executed onto the database | Low | High | Alex Bradford | Ensure that there is correct form validation for the database user input and data sanitization. Higher levels of protection can be included by prepared statements and parameterization
Application breaking bugs could be pushed live | With Agile/DevOps working the application is constantly being pushed live as it is being worked on. If there is improper source control management and testing, there could be application breaking bugs included in the updates. | Medium | Medium | Alex Bradford | Use source control mamagement tools such as github to enable code tracking and rollback. Ensure new code is pushed to dev branch and tests are ran before code is merged to main
DDoS Attack | Database server is communicated to via the internet, leaving it susceptible to a DDoS attack which could take it down/impeed performance | Low | High | Alex Bradford | Ensure AWS security groups to only allow ingress via the required ports/ip ranges. Further prevention could involve extra AWS services such as AWS Shield which provided DDoS protection. Use of CDN distribution could also help prevent attacks (CloudFront/CloudFlare)
Malware | Potential Malware on developer laptop could spread to instance/keylogger can reveal DB secrets causing unwanted access. | Low | High | Alex Bradford | AV Scanning on developer laptops and firewalls to prevent malware.